# 9 Legal Ethical Privacy Security and Policy Constraints

The project involves asset ownership, user identities, procurement values, maintenance history, photographs, documents, and AI service providers. These create legal and policy questions even in a prototype. UAE data protection law establishes requirements for maintaining the confidentiality of personal data, controlling how it is collected and processed, protecting individual rights, and managing cross-border data transfers. Khalifa University's public privacy page states that the institution uses security measures for personal information and limits disclosure to trusted parties and other permitted situations. This does not make a legal compliance determination. It identifies controls and approvals needed before real data or institutional systems are used.

Table 9 Constraint and Control Matrix

| Constraint | Project Exposure | Required Control |
| --- | --- | --- |
| Personal data | Names, accounts, activity history, contact information | Collect only necessary fields, control access, define purpose and retention, use approved data |
| Cross-border AI processing | Prompts or records may be sent to an external provider | Do not send restricted data without review of provider location, terms, retention, and approval |
| Asset ownership and transfer authorization | A recommendation could be mistaken for authority to transfer | Require authorized approval and receipt confirmation and preserve ownership history |
| Procurement and finance | Prices, budgets, savings, and supplier data may be confidential | Limit access, document data source, and separate sample values from actual records |
| Safety and hazardous assets | Some equipment may require inspection, certification, or specialist disposal | Flag restricted categories and prevent automated release or disposal |
| Intellectual property | Uploaded documents, images, model outputs, and code may have usage limits | Use approved content and licenses and record source and ownership |
| Security and audit | Unauthorized edits could change ownership, status, or decisions | Backend authorization, protected logs, secure sessions, validation, and access review |
| University policy | Internal acceptable-use, identity, data, network, and procurement rules apply | Consult current policy owners before integration or pilot deployment |

## 9. 1 Ethical Use of AI

The ethical boundary is straightforward: AI may help people find, classify, compare, and explain resources, but accountable users make consequential decisions. Every recommendation should show the main factors, confidence or uncertainty, and the model or rule version. Users must be able to reject the recommendation and provide a reason.

## 9. 2 Privacy by Design

The prototype should avoid unnecessary personal fields. Access tests should verify that a requester cannot view another user's restricted activity, a department representative cannot approve an action outside the assigned role, and an external AI request does not include information that the model does not need. Logs should record relevant actions without copying full prompts or sensitive documents by default.

# 10 Risk Assessment

The risk assessment combines the concerns raised in Phase 1 with the additional data, AI, privacy, and policy risks. Likelihood and impact use a five-point scale. The score is likelihood multiplied by impact. Values from 15 to 25 require immediate treatment, values from 8 to 14 require planned mitigation and monitoring, and lower values remain in the register for review.

Table 10 Risk Register

| Risk | L | I | Score | Mitigation |
| --- | --- | --- | --- | --- |
| Scope exceeds two-person capacity | 4 | 5 | 20 | Finalize the essential scope and postpone optional features that could delay the core workflow. |
| Usable institutional data is unavailable | 4 | 4 | 16 | Use synthetic or approved anonymized data |
| AI matches are irrelevant or unstable | 3 | 4 | 12 | Create labeled evaluation set, store versions, retain filters and manual selection |
| External AI cost exceeds the plan | 3 | 3 | 9 | Cut back on AI functions |
| Privacy or policy violation | 2 | 5 | 10 | Minimize collected data, review service terms and obtain approval before real data |
| Unauthorized ownership or status change | 2 | 5 | 10 | Apply backend authorization, separate approval responsibilities and maintain protected audit records. |
| Integration work begins too late | 4 | 4 | 16 | Define interfaces during design and complete an early end-to-end demonstration |
| Sustainability figures are misleading | 3 | 4 | 12 | Note assumptions and possibilities and increase storage units |
| Safety restricted asset is released | 2 | 5 | 10 | Flag restricted asset categories and require inspection and authorized approval. |
| Final testing time is compressed | 4 | 4 | 16 | Test throughout development, automate repeatable checks and reserve the final week for corrections. |

## 10. 1 Highest Priority Responses

The highest risks are schedule and data related. The team should respond before development by approving the minimum scope, generating a representative synthetic dataset, defining interfaces between application and AI modules, and preparing a working environment that either member can run. These controls reduce several risks at once because they make parallel work possible and prevent late discovery that the AI or workflow depends on missing information.